## Activity checklist
| TIMELINE | [18 empty] | RACI matrix
<Enter start date in cell B2> | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | <Your company> or consultant | [6 empty] | Discovery tool vendor
Activities | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | Discovery lead | Discovery engineer | Project manager | Infra | Application owner | Security and compliance | Network admin | Support 1 | Support 2
Planning
Select an automated discovery tool
Prepare discovery tool network requirements (port, IP address, firewall, routing)
Prepare discovery tool account requirements
Prepare and review pre-deployment checklist
Prepare the complete list of subnets or IP addresses to scan (by segment and by environment)
Prepare the required resources for the discovery tool, such as servers or virtual machines (VMs)
All required change orders have been approved and implemented
Infrastructure setup and configuration
Prepare the servers or VM platforms with resources required by the tool
Collect VMware vCenter, ESX, or ESXi IP address information and credentials
Provision network requirements for the discovery tool, such as IP address, port, firewall, and routing requirements
Collect IP address ranges for the hosts you want to scan
Establish outbound Internet access (proxy-free) for TCP/443
Establish required network access to all devices targeted for discovery
At least one test IP address available (such as a known system or device) for each credential, to test against during bootstrapping procedures
Provision credentials for the discovery tool. Enable only what is required
(As needed) Identify SNMP credentials for network devices targeted for discovery
(As needed) Identify SSH or read-only SNMP credentials for all Linux or Unix hosts that are targeted for discovery
Identify Windows domain administrator credentials for all Windows hosts that are targeted for discovery. For workgroup servers, collect local administrator credentials.
All applicable SSH, SNMP, Windows, and VMware vCenter credentials have been tested and validated
Deploy the agents (for an agent-based tool) or discovery appliance server (for an agentless tool)
Non-production discovery and inventory
Create non-production scan targets
Review assets and errors
(Optional) Request for rescan
Make a go or no-go decision for collecting non-production data
Non-production performance data collection
License target devices for data collection. Feature licensing is not required.
Review the assets
Review errors, debug, troubleshoot, and fix
(Optional) Request for rescan
Build, review, and refine the application stacks (only licensed devices will be placed in group)
Make a go or no-go decision for expanding to production
Production discovery and inventory
Create production scan targets
Review the assets
Review errors, debug, troubleshoot, and fix
(Optional) Request for rescan
Make a go or no-go decision for collecting production data
Production performance data collection
License target devices for data collection. Feature licensing is not required.
Review the assets
Review errors, debug, troubleshoot, and fix
(Optional) Request for rescan
Build, review, and refine application stacks (only licensed devices will be placed in group)
Review overall portfolio of applications and their environments
Stop the discovery tool
Get approval to stop the discovery
Stop discovery in the discovery tool
Deactivate credentials
Optimization and licensing assessment (OLA) report generation and review
Review total cost of ownership (TCO) report
If available in your discovery tool, review the IaaS cloud pricing report to select the best instance type for your data
If available in your discovery tool, review the application prioritization reports, such as the Flexera Rscore and Optimization score card
Benefit-cost analysis report
Consolidate the cost reports, such as TCO and IAAS cloud pricing
Prepare benefit-cost analysis presentation