## Pre-migration
Pre-migration tasks |  | Primary task owner | Wave
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Open wave plan document | [8 empty] | Key
2 | Confirm the wave plan and validate the migration metadata | [8 empty] | I | In progress
3 | Submit an RFC for <placeholder> | [8 empty] | R | Risk accepted
4 | Send communitcation to app owners
5
6
7
8
Proceed to next phase?

## Migration
Migration tasks |  |  | Primary task owner | Wave
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Week 1: Data Import | 1 | Connect to the migration execution server
| 2 | Prepare the migration intake form and import data into CloudEndure Migration Factory | [8 empty] | Key
Week 1: Build the servers | 3 | Check the prerequisites | [8 empty] | C | Complete
| 4 | Install the replication agent | [8 empty] | I | In progress
| 5 | Push the post-launch script | [8 empty] | R | Risk accepted
Week 2: Validate the migration | 6 | Verify replication status
| 7 | Create the local admin user
| 8 | Validate the launch template
Week 3: Perform migration boot-up testing | 9 | Launch instances for boot-up testing
| 10 | Verify the target EC2 instance 2/2 status
| 11 | Mark as ready for cutover
12
13
14
15
16
Proceed to next phase?

## Cutover
Cutover tasks |  |  | Primary task owner | Estimated time | Wave
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Cutover tasks | 1 | Kick-off call with migration team and application representatives
| 2 | Verify replication status
| 3 | Stop services on source servers
| 4 | Shutdown source servers
| 5 | Launch cutover instances from CloudEndure Migration Factory | [9 empty] | Key
| 6 | Verify target instance boot up status | [9 empty] | C | Complete
| 7 | Retrieve the IP address of the target instance | [9 empty] | I | In progress
| 8 | Update DNS server | [9 empty] | R | Risk accepted
| 9 | Test target instance RDP/SSH access
| 10 | Target instance cleanup and Validate post launch scripts executed successfully
| 11 | Application and networking change for cutover
| 12 | Application testing
Integration testing (connections to upstream and downstream dependencies)
Validate there are no latency requirements (if applicable)
Validate network aspects are working as expected (i.e. NFS)
Perform smoke testing
Application validation agreement
| 13 | Enable Amazon EC2 termination protection
| 14 | Remove the local admin user
| 15 | Determine if migration was a success
| 16 | Close the change record
| 17 | Hand over to support teams
Roll-back tasks | 1 | Agreement to initiate roll back (vs roll forward)
| 2 | Shut down the EC2 instance
| 3 | Turn on source machine
| 4 | (If applicable) copy deltas in data to source machine
| 5 | Connections reverted to source infrastructure (i.e. DNS/ load balancer updates)
| 6 | Application rollback validation
| 7 | Schedule root cause analysis
Proceed to next phase?

## Post-migration
Post-migration tasks |  | Primary task owner | Wave
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Verify AWS Systems Manager Agent (SSM Agent) installation was successful
Verify monitoring tooling
Verify alerting tooling
| Verify logging tooling | [8 empty] | Key
| Update DNS TTL to original value | [8 empty] | C | Complete
| Performance testing | [8 empty] | I | In progress
| Simulate failure scenario | [8 empty] | R | Risk accepted
Test DR scenario
Test restore from backup
Licensing requirements? (e.g. Oracle CPU core)
Update documentation
Decomissioning source infrastructure
Use VPC flow logs to monitor dependencies on-premises
Migration wave complete?
Please note, the tasks on this tab vary based on the organization. Tasks are provided as an example, but it's recommended that you customize this tab for your use case.